## Action items
Category | status | Assign | Comments
Customer_656_na | Completed | Kishore and bharat | tested
Customer_na | Completed | Kishore and bharat | Yet to be test
plant_na | Completed | Kishore and bharat | Yet to be test
How the adhoc run geeting run | completed | siva
I have customer code how to test show me how can we can do that? | in progress | siva
Recording to the local system | in progress | Kishore and bharat
configuration file setup | in progress | Kishore and bharat
python wheel file | in progress | Kishore and bharat
Customer_na | in progress | siva | dim-customer table yet to be chceck
plant_na | in progress | siva | dim-customer table yet to be chceck
vendor_na | in progress | Kishore and bharat
sales_org_na | in progress | Kishore and bharat
product1_na | in progress | Kishore and bharat

## Delivered
Category | status | Assign | Comments
Customer_656_na | Completed | Kishore and bharat | Yet to be test
Customer_na | Completed | Kishore and bharat | Yet to be test
plant_na | Completed | Kishore and bharat | Yet to be test

## Yet to be deliver
Category | status | Assign | Comments
configuration file setup | in progress | Kishore and bharat
python wheel file | in progress | Kishore and bharat
pipeline migration | scope | status | Comments
1.Transfix_MD | current | in progress | Priority 1
2.Transfix_calc | upcomming | not yet started | Priority 2
3.Transfix_RGVR | yet to be | not yet started | yet to be discuss and analyse